## Sheet1
| Project Name | Completion | Project Budget | Measure U Allocation | Other Funding | Measure U Expenditures as of 6/30/07
A | Purchase of BAE Airport Site | Completed | 33000000 | 33000000 | 0 | 33000000
B | Emeritus College Facility | Completed | 9603782 | 8909940 | 693842 | 8909940
C | Purchase of 1738 Pearl Street | Completed | 749208 | 749208 | 0 | 749208
D | PE Temp. Bldg. Replacement | Completed | 2797033 | 2797033 | 0 | 2797033
E | Remodel Library Village for Math | Completed | 1458690 | 1458690 | 0 | 1458690
F | SM Airport Campus Site Improvements | Completed | 4170264 | 4170264 | 0 | 4170264
G | SM Airport Campus West Building | Completed | 19709741 | 19709741 | 0 | 19709741
H | Theater Arts Renovation | Completed | 19492296 | 19492296 | 0 | 19466484
I | Earthquake Rpl. Liberal Arts North | Completed | 12473652 | 5352752 | 7120900 | 8149467
J | Music Complex | Completed | 4300000 | 1700000 | 2600000 | 1634354
K | Earthquake Rpl. Liberal Arts South | Completed | 15891384 | 5266314 | 10625070 | 4933816
L | Shuttle Replacement Parking | Completed | 18510000 | 18510000 | 0 | 18360515
M | North Quad Plaza | December 2008 | 9493568 | 9493568 | 0 | 834197
N | Letters & Sci Demo/Restore | On Hold | 0 | 0 | 0 | 0
O | Student Services Building | March 2012 | 48767834 | 20213268 | 28554566 | 777817
P | Science Complex Addition | On Hold | 308000 | 308000 | 0 | 277536
Q | Infrastructure & Safety | 2008 | 6859518 | 6859518 | 0 | 2247780
R | Restroom Improvements | 2008 | 100000 | 85000 | 0 | 17501
S | Master Planning | 2008 | 1605166 | 1605166 | 0 | 1105166
T | 14th and Pico Project | On Hold | 319242 | 319242 | 0 | 319242
| Project Totals |  | 209609378 | 160000000 | 49594378 | 128918751