## Sheet1
| Project Name | Completion | Project Budget | Measure U Allocation | Other Funding | Measure U Expenditures as of 9/30/08 | Measure U Expenditures as of 6/30/08 | Measure U Expenditures Last Period
A | Purchase of BAE Airport Site | Completed | 30280878 | 30280878 | 0 | 30280878 | 30280878 | 0
B | Emeritus College Facility | Completed | 9603782 | 8909940 | 693842 | 8909940 | 8909940 | 0
C | Purchase of 1738 Pearl Street | Completed | 749208 | 749208 | 0 | 749208 | 749208 | 0
D | PE Temp. Bldg. Replacement | Completed | 2797033 | 2797033 | 0 | 2797033 | 2797033 | 0
E | Remodel Library Village for Math | Completed | 1458690 | 1458690 | 0 | 1458690 | 1458690 | 0
F | SM Airport Campus Site Improvements | Completed | 4170264 | 4170264 | 0 | 4170264 | 4170264 | 0
G | SM Airport Campus West Building | Completed | 19709741 | 19709741 | 0 | 19709741 | 19709741 | 0
H | Theater Arts Renovation | Completed | 19569266 | 19569266 | 0 | 19491704 | 19491704 | 0
I | Earthquake Rpl. Liberal Arts North | Completed | 13473652 | 6352752 | 7120900 | 8449131 | 8448095 | 1036
J | Music Complex | Completed | 5585534 | 2967421 | 2618113 | 1968671 | 1967421 | 1250
K | Earthquake Rpl. Liberal Arts South | Completed | 16891384 | 6266314 | 10625070 | 5987506 | 5978051 | 9455
L | Shuttle Replacement Parking | Completed | 18967156 | 18967156 | 0 | 18967156 | 18967156 | 0
M | North Quad Plaza | October 2008 | 11493568 | 11493568 | 0 | 9294854 | 7446745 | 1848109
N | Letters & Sci Demo/Restore | Future Project | 0 | 0 | 0 | 0 | 0 | 0
O | Student Services Building | April 2012 | 94027100 | 15940124 | 78086976 | 895256 | 872083 | 23173
P | Science Complex Addition | Future Project | 308000 | 308336 | 0 | 308336 | 308336 | 0
Q | Infrastructure & Safety | 2008 | 7649901 | 7649901 | 0 | 2334635 | 2327115 | 7520
R | Restroom Improvements | 2008 | 85000 | 85000 | 0 | 17501 | 17501 | 0
S | Master Planning | 2008 | 2005166 | 2005166 | 0 | 1527686 | 1469991 | 57695
T | 14th and Pico Project | On Hold | 319242 | 319242 | 0 | 319242 | 319242 | 0
| Project Totals |  | 259144565 | 160000000 | 99144901 | 137637432 | 135689194 | 1948238